## Sheet1
Minimum Testing Requirements
| Key Number |  | Project Number |  | Project Name |  |  |  | Work Authority
| Contract Number |  |  |  |  | Contractor
| CE&I Project Manger |  |  |  |  | Resident Engineer
Acceptance of material will be according to the contract, plans and specifications, including the ITD QA Manual. The number of samples taken shall not be determined exclusively by this schedule, but shall represent the quantity used as required by the minimum test requirements for acceptance and the Independent Assurance Program.
| BID # | MATERIAL | PURPOSE OF TESTING | SPEC. REF. | TEST METHOD | REQUIRED REPORT FORM NO. | MINIMUM FREQUENCY | REMARKERS, NOTES, OR ADDITIONAL INSTRUCTIONS | BID QUANTITY | MINIMUM NO. TESTS/ CERTS REQ. | # COMPLETED/ QUANTITY CERTIFIED | VERIFIED BY (CONSULTANT INITIALS)
|  |  |  | SAMPLED BY | TESTED BY
BID ITEM NO. & DESCRIPTION: 201-010A - Clearing & Grubbing
| 201-010A | Clearing & Grubbing |  | No Testing Required | No Testing Required | ITD-854 | Total Quantity Paid | Check Approved Waste Sites. RE Letter-See QA Manual Section 250.00 | 1 LS | RE-LETTER
BID ITEM NO. & DESCRIPTION: 107-019A Monument Preservation
X | 107-019A | Mounument Preservation | ACCEPTANCE Inspection | No Testing Required | No Testing Required | ITD-854 | Total Quantity Paid | RE Letter-See QA Manual Section 250.00 | 2,000 CA
|  | Test No. | Test Date | Form Used | Accept/ Verif. | Qty. | P/F | Remarks
X | BID ITEM NO. & DESCRIPTION: 201-010A Clearing & Grubbing
X | 201-010A | Clearing & Grubbing | ACCEPTANCE Inspection | No Testing Required | No Testing Required | ITD-854 | Total Quantity Paid | RE Letter-See QA Manual Section 250.00 | 1 LS
|  | Test No. | Test Date | Form Used | Accept/ Verif. | Qty. | P/F | Remarks
X | BID ITEM NO. & DESCRIPTION: 203-015A Rem of Bituminous Surf
| 203-015A | Rem of Bituminous Surf | ACCEPTANCE Inspection | No Testing Required | No Testing Required | ITD-854 | Total Quantity Paid | RE Letter-See QA Manual Section 250.00 | 5,171 SY
|  | Test No. | Test Date | Form Used | Accept/ Verif. | Qty. | P/F | Remarks
X | BID ITEM NO. & DESCRIPTION: 203-075A Rem of Fence
| 203-075A | Rem of Fence | ACCEPTANCE Inspection | No Testing Required | No Testing Required | ITD-854 | Total Quantity Paid | RE Letter-See QA Manual Section 250.00 | 182 FT
X
|  | Test No. | Test Date | Form Used | Accept/ Verif. | Qty. | P/F | Remarks
BID ITEM NO. & DESCRIPTION: 203-125C Rem of Misc Items (Pipe Culvert)
| 203-125C | Rem oF Misc Items | ACCEPTANCE Inspection | No Testing Required | No Testing Required | ITD-854 | Total Quantity Paid | RE Letter-See QA Manual Section 250.00 | 246 FT
|  | Test No. | Test Date | Form Used | Accept/ Verif. | Qty. | P/F | Remarks
BID ITEM NO. & DESCRIPTION: 203-130A Removal of Pav Markings
| 203-130A | Rem of Pav Markings | ACCEPTANCE Inspection | No Testing Required | No Testing Required | ITD-854 | Total Quantity Paid | RE Letter-See QA Manual Section 250.00 | 598 FT
|  | Test No. | Test Date | Form Used | Accept/ Verif. | Qty. | P/F | Remarks
X | BID ITEM NO. & DESCRIPTION: 203-135A Removal of Signs
X | 203-135A | Rem of Signs | ACCEPTANCE Inspection | No Testing Required | No Testing Required | ITD-854 | Total Quantity Paid | RE Letter-See QA Manual Section 250.00 | 3 EA
|  | Test No. | Test Date | Form Used | Accept/ Verif. | Qty. | P/F | Remarks
X | BID ITEM NO. & DESCRIPTION: 205-005A Excavation
| 205-005A | Excavation | ACCEPTANCE In-Place Density | 205.03 F | AASHTO T 99 AASHTO T 180AASHTO T 272 Idaho IT-74 | ITD-850 | Each 2,500 CY or 4,000 tons but not less than 1 test per lift for each bottom 3 and each top 3 lifts and 1 test every 2,500 CY or 4,000 tons in between. | Document compaction effort (equipment, number of passes etc.) for lifts not tested. After remedial efforts, obtain check tests within 10 feet and at same depth as original test. | 34,095 CY
|  |  |  | ITD Project Personnel | ITD Project Personnel
|  | Test No. | Test Date | Form Used | Accept/ Verif. | Qty. | P/F | Remarks
BID ITEM NO. & DESCRIPTION: 205-060A Water for Dust Abatement
| 205-060A | Dust Abatement | ACCEPTANCE Inspection | No Testing Required | No Testing Required | ITD-854 | Total Quantity Paid | RE Letter-See QA Manual Section 250.00 | 100 MG
|  | Test No. | Test Date | Form Used | Accept/ Verif. | Qty. | P/F | Remarks
BID ITEM NO. & DESCRIPTION: 208-005A Interceptor Ditch
| 208-005A | Interceptor Ditch | ACCEPTANCE Inspection | No Testing Required | No Testing Required | ITD-854 | Total Quantity Paid | RE Letter-See QA Manual Section 250.00 | 5.510 STA
|  | Test No. | Test Date | Form Used | Accept/ Verif. | Qty. | P/F | Remarks
BID ITEM NO. & DESCRIPTION: 212-011A Fiber Wattle
| 212-011A | Fiber Wattle | ACCEPTANCE Certification | 711.2 |  | ITD-851 | Total Quantity Paid | Certified Noxious weed-free grain straw | 5,627 FT
|  |  |  | Manufacturer | Manufacturer
|  | Test No. | Test Date | Form Used | Accept/ Verif. | Qty. | P/F | Remarks
BID ITEM NO. & DESCRIPTION: 212-020A Silt Fence
| 212-020A | Silt Fence | ACCEPTANCE Certification | 212.03-B 718.09 |  | ITD-849 | Total Quantity Paid | See QA Manual Section 230.09 | 31 FT
|  |  |  | Manufacturer | Manufacturer
|  | Test No. | Test Date | Form Used | Accept/ Verif. | Qty. | P/F | Remarks
BID ITEM NO. & DESCRIPTION: 212-060a Stabilized Construction Entrance
| 212-060A | Stabilized Construction Entrance | ACCEPTANCE Certification | 212.03-B |  | ITD-849 | Total Quantity Paid | See QA Manual Section 230.09 | 2 EA
|  |  |  | Manufacturer | Manufacturer
|  | Test No. | Test Date | Form Used | Accept/ Verif. | Qty. | P/F | Remarks
BID ITEM NO. & DESCRIPTION: 212-105A Water Pollution & Erosion Control
| 212-105A | Water Pollution & Erosion Control | ACCEPTANCE Inspection | No Testing Required | No Testing Required | ITD-854 | Total Quantity Paid | RE Letter-See QA Manual Section 250.00 | 5,000 CA
|  | Test No. | Test Date | Form Used | Accept/ Verif. | Qty. | P/F | Remarks
BID ITEM NO. & DESCRIPTION: 301-005A Granular Subbase
| 301-005A | Granular Subbase | ACCEPTANCE Visual Inspection | No Testing Required | No Testing Required | ITD-851 | Total Quantity Paid | Small Quantity - compaction effort and equipment noted on daily diary | 4,403 TON
|  | Test No. | Test Date | Form Used | Accept/ Verif. | Qty. | P/F | Remarks
BID ITEM NO. & DESCRIPTION: 303-021A 3/4" AGGR TY A for Base
| 303-021A | 3/4" Agg TY A For Base | ACCEPTANCE Visual Inspection | No Testing Required | No Testing Required | ITD-851 | Total Quantity Paid | Small Quantity - compaction effort and equipment noted on daily diary | 2,163 TON
|  | Test No. | Test Date | Form Used | Accept/ Verif. | Qty. | P/F | Remarks
BID ITEM NO. & DESCRIPTION: 401-020A CSS-1 DIL EMUL ASPH for Tack Coat
| 401-020A | Dil Emul Asphalt for Tack Coat | ACCEPTANCE Certification | 702.03 702.05 | *No Testing Required | Loading Cert | Each individual truck, trailer, car or shipment to the project. | *No ITD-1045 when project quanity is less than 2,000 Gallons | 545 GAL
|  | Test No. | Test Date | Form Used | Accept/ Verif. | Qty. | P/F | Remarks
BID ITEM NO. & DESCRIPTION: 405-245A Approach (Farm Field)
| 405-245A | Approach | ACCEPTANCE Inspection | No Testing Required | No Testing Required | ITD-854 | Total Quantity Paid | RE Letter-See QA Manual Section 250.00 | 2 EA
|  | Test No. | Test Date | Form Used | Accept/ Verif. | Qty. | P/F | Remarks
BID ITEM NO. & DESCRIPTION: 405-245B Approach (Public)
| 405-245B | Approach | ACCEPTANCE Inspection | No Testing Required | No Testing Required | ITD-854 | Total Quantity Paid | RE Letter-See QA Manual Section 250.00 | 1 EA
|  | Test No. | Test Date | Form Used | Accept/ Verif. | Qty. | P/F | Remarks
BID ITEM NO. & DESCRIPTION: 405-325A HMA Paving
| 405-325A | HMA Paving | ACCEPTANCE Visual Inspection | No Testing Required | No Testing Required | ITD-851 | Total Quantity Paid | Small Quantity - compaction effort and equipment noted on daily diary | 1,679 TON
|  | Test No. | Test Date | Form Used | Accept/ Verif. | Qty. | P/F | Remarks
BID ITEM NO. & DESCRIPTION: 602-035A 18" Pipe Culvert
| 602-35A | 18" Pipe Culvert | ACCEPTANCE Certification | 706.06 | AASHTO M 36 or AASHTO M 196 | ITD-914 with mill tests attached for steel/iron or ITD-851 for aluminum | Total Quantity Paid | See QA Manual Section 230.01 and Section 230.03 | 314 FT
|  |  |  | Manufacturer | Manufacturer
|  | Test No. | Test Date | Form Used | Accept/ Verif. | Qty. | P/F | Remarks
BID ITEM NO. & DESCRIPTION: 602-065A 36" Pipe Culvert
| 602-065A | 36" Pipe Culvert | ACCEPTANCE Certification |  | AASHTO M 36 or AASHTO M 196 | ITD-914 with mill tests attached for steel/iron or ITD-851 for aluminum | Total Quantity Paid | See QA Manual Section 230.01 and Section 230.03 | 52 FT
|  |  |  | Manufacturer | Manufacturer
|  | Test No. | Test Date | Form Used | Accept/ Verif. | Qty. | P/F | Remarks
BID ITEM NO. & DESCRIPTION: 602-065A 18" Apron for Pipe
| 608-035A | 18" Apron for Pipe | ACCEPTANCE Certification | 608 708.21 | AASHTO M 36 or AASHTO M 196 | ITD-914 with mill tests attached for steel/iron | Total Quantity Paid | See QA Manual Section 230.01 and Section 230.03 | 8 EA
|  |  |  | Manufacturer | Manufacturer
|  | Test No. | Test Date | Form Used | Accept/ Verif. | Qty. | P/F | Remarks
BID ITEM NO. & DESCRIPTION: 608-065A 36" Apron for Pipe
| 608-065A | 36" Apron for Pipe | ACCEPTANCE Certification | 608 708.21 | AASHTO M 36 or AASHTO M 196 | ITD-914 with mill tests attached for steel/iron | Total Quantity Paid | See QA Manual Section 230.01 and Section 230.03 | 1 EA
|  |  |  | Manufacturer | Manufacturer
|  | Test No. | Test Date | Form Used | Accept/ Verif. | Qty. | P/F | Remarks
BID ITEM NO. & DESCRIPTION: 610-015A Fence TY 1 B
| 610-015A | Fence TY 1B | ACCEPTANCE Certification | 708.09 |  | ITD-914 with mill tests attached for steel/iron | Total Quantity Paid | See QA Manual Section 230.01 and Section 230.03 | 127 FT
|  |  |  | Manufacturer | Manufacturer
|  | Test No. | Test Date | Form Used | Accept/ Verif. | Qty. | P/F | Remarks
BID ITEM NO. & DESCRIPTION: 616-010A Signs TY B
| 616-010A | Signs TY B | ACCEPTANCE Certification | Sheet Aluminum 708.27 |  | ITD-851 | Total Quantity Paid | See QA Manual Section 230.01 | 20 SF
|  |  |  | Manufacturer | Manufacturer
|  | Test No. | Test Date | Form Used | Accept/ Verif. | Qty. | P/F | Remarks
BID ITEM NO. & DESCRIPTION: 616-035A Sign Brackets & Brace Angles
| 616-035A | Sign Brackets & Brace Angles | ACCEPTANCE Certification | 708.17-A |  | ITD-914 with mill tests attached for steel/iron | Total Quantity Paid | See QA Manual Section 230.01 and Section 230.03 | 17.6 LBS
|  |  |  | Manufacturer | Manufacturer
|  | Test No. | Test Date | Form Used | Accept/ Verif. | Qty. | P/F | Remarks
BID ITEM NO. & DESCRIPTION: 616-055A Breakaway Wood Sign Post TY D
| 616-055A | Breakaway Wood Sign Post TY D | ACCEPTANCE Certification | 710.02 710.09 |  | ITD-851 | Total Quantity Paid | See QA Manual Section 230.01 The manufacturer must provide a copy of the wood treatment certification | .030 MFBM
|  |  |  | Manufacturer | Manufacturer
|  | Test No. | Test Date | Form Used | Accept/ Verif. | Qty. | P/F | Remarks
BID ITEM NO. & DESCRIPTION: 617-015A Delineator TY 3
| 617-015A | Delineator TY 3 | ACCEPTANCE Certification | 708.16 |  | ITD-851 or ITD-914 with mill test reports attached for steel | Total Quantity Paid | See QA Manual Section 230.01 and Section 230.03 | 16 EA
|  |  |  | Manufacturer | Manufacturer
|  | Test No. | Test Date | Form Used | Accept/ Verif. | Qty. | P/F | Remarks
BID ITEM NO. & DESCRIPTION: 617-020A Delineator TY 4
| 617-020A | Delineator TY 4 | ACCEPTANCE Certification | 708.16 |  | ITD-851 or ITD-914 with mill test reports attached for steel | Total Quantity Paid | See QA Manual Section 230.01 and Section 230.03 | 4 EA
|  |  |  | Manufacturer | Manufacturer
|  | Test No. | Test Date | Form Used | Accept/ Verif. | Qty. | P/F | Remarks
BID ITEM NO. & DESCRIPTION: 621-005A Seed Bed Preparation
| 621-005A | Seed Bed Prep | ACCEPTANCE Inspection | No Testing Required | No Testing Required | ITD-854 | Total Quantity Paid | RE Letter-See QA Manual Section 250.00 | 3.89 ACRE
|  | Test No. | Test Date | Form Used | Accept/ Verif. | Qty. | P/F | Remarks
BID ITEM NO. & DESCRIPTION: 621-010A Seeding
| 621-010A | Seeding | ACCEPTANCE Certification | 711.05 711.07 711.10 711.11 711.12 711.16 |  | ITD-851 with Laboratory Analysis Report Attached | Total Quantity Paid |  | 3.89 ACRE
|  |  |  | Manufacturer | Manufacturer
|  | Test No. | Test Date | Form Used | Accept/ Verif. | Qty. | P/F | Remarks
BID ITEM NO. & DESCRIPTION: 621-015A Mulching
| 621-015A | Mulching | ACCEPTANCE Certification | 711.05 711.07 711.10 711.11 711.12 711.16 |  | ITD-851 with Laboratory Analysis Report Attached | Total Quantity Paid |  | 3.89 ACRE
|  |  |  | Manufacturer | Manufacturer
|  | Test No. | Test Date | Form Used | Accept/ Verif. | Qty. | P/F | Remarks
BID ITEM NO. & DESCRIPTION: 621-025A Mulch Anchoring (Tackifier)
| 621-025A | Much Anchoring (Tackifier) | ACCEPTANCE Certification | 711.05 711.07 711.10 711.11 711.12 711.16 |  | ITD-851 with Laboratory Analysis Report Attached | Total Quantity Paid |  | 3.89 ACRE
|  |  |  | Manufacturer | Manufacturer
|  | Test No. | Test Date | Form Used | Accept/ Verif. | Qty. | P/F | Remarks
BID ITEM NO. & DESCRIPTION: 624-005A Loose Riprap
| 624-005A | Loose RipRap | ACCEPTANCE Inspection | 711.04 | Visual Inspection | ITD-0854 | Total Quantity Paid | Initial testing required for Apparent Specific Gravity, Absorption, (AASHTO T 85) and Coarse durability Index, (AASHTO T 210). Only visual inspection during placement. | 73.7 CY
|  | Test No. | Test Date | Form Used | Accept/ Verif. | Qty. | P/F | Remarks
BID ITEM NO. & DESCRIPTION: 626-010A Temp Traffic Control Signs
| 626-010A | Temp Traffic Control Signs | ACCEPTANCE Certification | Reflectivity 712.02 |  | ITD-851 | Total Quantity Paid | Must meet NCHRP-350 | 416 SF
|  | Test No. | Test Date | Form Used | Accept/ Verif. | Qty. | P/F | Remarks
BID ITEM NO. & DESCRIPTION: 626-040A Barricade TY 3
| 626-040A | Barricade TY 3 | ACCEPTANCE Certification | Reflectivity 712.02 |  | ITD-851 | Total Quantity Paid | Must meet NCHRP-350 | 5 EA
|  | Test No. | Test Date | Form Used | Accept/ Verif. | Qty. | P/F | Remarks
BID ITEM NO. & DESCRIPTION: 626-050A Drums
| 626-050A | Drums | ACCEPTANCE Certification | Reflectivity 712.02 |  | ITD-851 | Total Quantity Paid | Must meet NCHRP-350 | 20 EA
|  | Test No. | Test Date | Form Used | Accept/ Verif. | Qty. | P/F | Remarks
BID ITEM NO. & DESCRIPTION: 626-100A Misc Temporary Traf Cont Items
| 626-100A | Temp Traffic Control Items | ACCEPTANCE Certification | Reflectivity 712.02 |  | ITD-851 | Total Quantity Paid | Must meet NCHRP-350 | 1 LS
|  | Test No. | Test Date | Form Used | Accept/ Verif. | Qty. | P/F | Remarks
BID ITEM NO. & DESCRIPTION: 626-105A Traffic Control Maintenance
| 626-105A | Traffic Control Maintenance | ACCEPTANCE Inspection | No Testing Required | No Testing Required | ITD-854 | Total Quantity Paid | RE Letter-See QA Manual Section 250.00 | 680 HR
|  | Test No. | Test Date | Form Used | Accept/ Verif. | Qty. | P/F | Remarks
BID ITEM NO. & DESCRIPTION: 626-120A Flagger Control
| 626-120A | Flagger Control | ACCEPTANCE Inspection | No Testing Required | No Testing Required | ITD-854 | Total Quantity Paid | RE Letter-See QA Manual Section 250.00 | 100 HR
|  | Test No. | Test Date | Form Used | Accept/ Verif. | Qty. | P/F | Remarks
BID ITEM NO. & DESCRIPTION: 626-135A Weighted Base Tubular Markers
| 626-135A | Weighted Base Tubular Markers | ACCEPTANCE Certification | Reflectivity 712.02 |  | ITD-851 | Total Quantity Paid | Must meet NCHRP-350 | 10 EA
|  | Test No. | Test Date | Form Used | Accept/ Verif. | Qty. | P/F | Remarks
BID ITEM NO. & DESCRIPTION: 630-020B Pav MkG - Preformed Theromoplastic
| 630-020B | Preformed Thermoplastic | ACCEPTANCE Certification |  |  | ITD-851 | Total Quantity Paid | See QA Manual Section 230.01 | 57 EA
|  |  |  | Manufacturer | Manufacturer
|  | Test No. | Test Date | Form Used | Accept/ Verif. | Qty. | P/F | Remarks
BID ITEM NO. & DESCRIPTION: 630-025A Longitudinal Pav Markings Waterborne
| 630-025A | Pave Markings Waterborne | ACCEPTANCE Laboratory Tests |  |  | ITD-1830 for Paint ITD-1828 for Beads | Total Quantity Paid | Each Lot used on Project | 7,071 FT
|  |  |  | Manufacturer | Manufacturer
|  | Test No. | Test Date | Form Used | Accept/ Verif. | Qty. | P/F | Remarks
BID ITEM NO. & DESCRIPTION: 640-010A Riprap Erosion Control Geotextile
| 640-010A | RipRap Erosion Geotextile | ACCEPTANCE Certification | 718.06 |  | ITD-849, ITD-1044, ITD-1047 | Total Quantity Paid | See QA Manual Section 230.09 | 430 SY
|  |  |  | Manufacturer/ ITD Project Personnel | Manufacturer/ ITD Central Lab
|  | Test No. | Test Date | Form Used | Accept/ Verif. | Qty. | P/F | Remarks
BID ITEM NO. & DESCRIPTION: 675-005A Survey
| 675-005A | Survey | ACCEPTANCE Inspection | No Testing Required | No Testing Required | ITD-854 | Total Quantity Paid | RE Letter-See QA Manual Section 250.00 | 1 LS
|  | Test No. | Test Date | Form Used | Accept/ Verif. | Qty. | P/F | Remarks
BID ITEM NO. & DESCRIPTION: 675-010A Directed Surveying Office Computations
| 675-010A | Directed Surveying Office Comp | ACCEPTANCE Inspection | No Testing Required | No Testing Required | ITD-854 | Total Quantity Paid | RE Letter-See QA Manual Section 250.00 | 2,000 CA
|  | Test No. | Test Date | Form Used | Accept/ Verif. | Qty. | P/F | Remarks
BID ITEM NO. & DESCRIPTION: 675-015A Directed Surveying Crew
| 675-010A | Directed Surveying Crew | ACCEPTANCE Inspection | No Testing Required | No Testing Required | ITD-854 | Total Quantity Paid | RE Letter-See QA Manual Section 250.00 | 2,000 CA
|  | Test No. | Test Date | Form Used | Accept/ Verif. | Qty. | P/F | Remarks
BID ITEM NO. & DESCRIPTION: S900-50A CA Misc Work
| S900-50A | Misc Work | ACCEPTANCE Inspection | No Testing Required | No Testing Required | ITD-854 | Total Quantity Paid | RE Letter-See QA Manual Section 250.00 | 5,000 CA
|  | Test No. | Test Date | Form Used | Accept/ Verif. | Qty. | P/F | Remarks
BID ITEM NO. & DESCRIPTION: Z629-05A Mobilization
| Z629-05A | Mobilization | ACCEPTANCE Inspection | No Testing Required | No Testing Required | ITD-854 | Total Quantity Paid | RE Letter-See QA Manual Section 250.00 | 1 LS
|  | Test No. | Test Date | Form Used | Accept/ Verif. | Qty. | P/F | Remarks