## Sheet1
Minimum Testing Requirements
| Key Number |  | Project Number |  | Project Name |  |  |  | Work Authority
| Contract Number |  |  |  |  | Contractor
| CE&I Project Manger |  |  |  |  | Resident Engineer
Acceptance of material will be according to the contract, plans and specifications, including the ITD QA Manual. The number of samples taken shall not be determined exclusively by this schedule, but shall represent the quantity used as required by the minimum test requirements for acceptance and the Independent Assurance Program.
| BID # | MATERIAL | PURPOSE OF TESTING | SPEC. REF. | TEST METHOD | REQUIRED REPORT FORM NO. | MINIMUM FREQUENCY | REMARKERS, NOTES, OR ADDITIONAL INSTRUCTIONS | BID QUANTITY | MINIMUM NO. TESTS/ CERTS REQ. | # COMPLETED/ QUANTITY CERTIFIED | VERIFIED BY (CONSULTANT INITIALS)
|  |  |  | SAMPLED BY | TESTED BY
BID ITEM NO. & DESCRIPTION: 201-010A - Clearing & Grubbing
| 201-010A | Clearing & Grubbing |  | No Testing Required | No Testing Required | ITD-854 | Total Quantity Paid | Check Approved Waste Sites. RE Letter-See QA Manual Section 250.00 | 1 LS | RE-LETTER
BID ITEM NO. & DESCRIPTION:
X
|  | Test No. | Test Date | Form Used | Accept/ Verif. | Qty. | P/F | Remarks
X | BID ITEM NO. & DESCRIPTION:
X
|  | Test No. | Test Date | Form Used | Accept/ Verif. | Qty. | P/F | Remarks
X | BID ITEM NO. & DESCRIPTION:
|  | Test No. | Test Date | Form Used | Accept/ Verif. | Qty. | P/F | Remarks
X | BID ITEM NO. & DESCRIPTION:
X
|  | Test No. | Test Date | Form Used | Accept/ Verif. | Qty. | P/F | Remarks
BID ITEM NO. & DESCRIPTION:
|  | Test No. | Test Date | Form Used | Accept/ Verif. | Qty. | P/F | Remarks
BID ITEM NO. & DESCRIPTION:
|  | Test No. | Test Date | Form Used | Accept/ Verif. | Qty. | P/F | Remarks
X | BID ITEM NO. & DESCRIPTION:
X
|  | Test No. | Test Date | Form Used | Accept/ Verif. | Qty. | P/F | Remarks
X | BID ITEM NO. & DESCRIPTION:
|  | Test No. | Test Date | Form Used | Accept/ Verif. | Qty. | P/F | Remarks
BID ITEM NO. & DESCRIPTION:
|  | Test No. | Test Date | Form Used | Accept/ Verif. | Qty. | P/F | Remarks
BID ITEM NO. & DESCRIPTION:
|  | Test No. | Test Date | Form Used | Accept/ Verif. | Qty. | P/F | Remarks
BID ITEM NO. & DESCRIPTION:
|  | Test No. | Test Date | Form Used | Accept/ Verif. | Qty. | P/F | Remarks
BID ITEM NO. & DESCRIPTION:
|  | Test No. | Test Date | Form Used | Accept/ Verif. | Qty. | P/F | Remarks
BID ITEM NO. & DESCRIPTION:
|  | Test No. | Test Date | Form Used | Accept/ Verif. | Qty. | P/F | Remarks
BID ITEM NO. & DESCRIPTION:
|  | Test No. | Test Date | Form Used | Accept/ Verif. | Qty. | P/F | Remarks
BID ITEM NO. & DESCRIPTION:
|  | Test No. | Test Date | Form Used | Accept/ Verif. | Qty. | P/F | Remarks
BID ITEM NO. & DESCRIPTION:
|  | Test No. | Test Date | Form Used | Accept/ Verif. | Qty. | P/F | Remarks
BID ITEM NO. & DESCRIPTION:
|  | Test No. | Test Date | Form Used | Accept/ Verif. | Qty. | P/F | Remarks
BID ITEM NO. & DESCRIPTION:
|  | Test No. | Test Date | Form Used | Accept/ Verif. | Qty. | P/F | Remarks
BID ITEM NO. & DESCRIPTION:
|  | Test No. | Test Date | Form Used | Accept/ Verif. | Qty. | P/F | Remarks
BID ITEM NO. & DESCRIPTION: 405-325A HMA Paving
|  | Test No. | Test Date | Form Used | Accept/ Verif. | Qty. | P/F | Remarks
BID ITEM NO. & DESCRIPTION:
|  | Test No. | Test Date | Form Used | Accept/ Verif. | Qty. | P/F | Remarks
BID ITEM NO. & DESCRIPTION:
|  | Test No. | Test Date | Form Used | Accept/ Verif. | Qty. | P/F | Remarks
BID ITEM NO. & DESCRIPTION:
|  | Test No. | Test Date | Form Used | Accept/ Verif. | Qty. | P/F | Remarks
BID ITEM NO. & DESCRIPTION:
|  | Test No. | Test Date | Form Used | Accept/ Verif. | Qty. | P/F | Remarks
BID ITEM NO. & DESCRIPTION:
|  | Test No. | Test Date | Form Used | Accept/ Verif. | Qty. | P/F | Remarks
BID ITEM NO. & DESCRIPTION:
|  | Test No. | Test Date | Form Used | Accept/ Verif. | Qty. | P/F | Remarks
BID ITEM NO. & DESCRIPTION:
|  | Test No. | Test Date | Form Used | Accept/ Verif. | Qty. | P/F | Remarks
BID ITEM NO. & DESCRIPTION:
|  | Test No. | Test Date | Form Used | Accept/ Verif. | Qty. | P/F | Remarks
BID ITEM NO. & DESCRIPTION:
|  | Test No. | Test Date | Form Used | Accept/ Verif. | Qty. | P/F | Remarks
BID ITEM NO. & DESCRIPTION:
|  | Test No. | Test Date | Form Used | Accept/ Verif. | Qty. | P/F | Remarks
BID ITEM NO. & DESCRIPTION:
|  | Test No. | Test Date | Form Used | Accept/ Verif. | Qty. | P/F | Remarks
BID ITEM NO. & DESCRIPTION:
|  | Test No. | Test Date | Form Used | Accept/ Verif. | Qty. | P/F | Remarks
BID ITEM NO. & DESCRIPTION:
|  | Test No. | Test Date | Form Used | Accept/ Verif. | Qty. | P/F | Remarks
BID ITEM NO. & DESCRIPTION:
|  | Test No. | Test Date | Form Used | Accept/ Verif. | Qty. | P/F | Remarks
BID ITEM NO. & DESCRIPTION:
|  | Test No. | Test Date | Form Used | Accept/ Verif. | Qty. | P/F | Remarks
BID ITEM NO. & DESCRIPTION:
|  | Test No. | Test Date | Form Used | Accept/ Verif. | Qty. | P/F | Remarks
BID ITEM NO. & DESCRIPTION:
|  | Test No. | Test Date | Form Used | Accept/ Verif. | Qty. | P/F | Remarks
BID ITEM NO. & DESCRIPTION:
|  | Test No. | Test Date | Form Used | Accept/ Verif. | Qty. | P/F | Remarks
BID ITEM NO. & DESCRIPTION:
|  | Test No. | Test Date | Form Used | Accept/ Verif. | Qty. | P/F | Remarks
BID ITEM NO. & DESCRIPTION:
|  | Test No. | Test Date | Form Used | Accept/ Verif. | Qty. | P/F | Remarks
BID ITEM NO. & DESCRIPTION:
|  | Test No. | Test Date | Form Used | Accept/ Verif. | Qty. | P/F | Remarks
BID ITEM NO. & DESCRIPTION: s
|  | Test No. | Test Date | Form Used | Accept/ Verif. | Qty. | P/F | Remarks
BID ITEM NO. & DESCRIPTION:
|  | Test No. | Test Date | Form Used | Accept/ Verif. | Qty. | P/F | Remarks
BID ITEM NO. & DESCRIPTION:
|  | Test No. | Test Date | Form Used | Accept/ Verif. | Qty. | P/F | Remarks
BID ITEM NO. & DESCRIPTION:
|  | Test No. | Test Date | Form Used | Accept/ Verif. | Qty. | P/F | Remarks
BID ITEM NO. & DESCRIPTION:
|  | Test No. | Test Date | Form Used | Accept/ Verif. | Qty. | P/F | Remarks
BID ITEM NO. & DESCRIPTION:
|  | Test No. | Test Date | Form Used | Accept/ Verif. | Qty. | P/F | Remarks
BID ITEM NO. & DESCRIPTION:
|  | Test No. | Test Date | Form Used | Accept/ Verif. | Qty. | P/F | Remarks
BID ITEM NO. & DESCRIPTION:
|  | Test No. | Test Date | Form Used | Accept/ Verif. | Qty. | P/F | Remarks
BID ITEM NO. & DESCRIPTION:
|  | Test No. | Test Date | Form Used | Accept/ Verif. | Qty. | P/F | Remarks