BOARD ORDER
from Bonneville County

Project No. A020(516) Key No. 20516
E RV RD (N 5TH W) CURVE IMPRV
BONNEVILLE COUNTY, IDAHO

CENTURY LINK (“Company”), having been informed of the project, executed a “Waiver of Hearing” on January 30, 2020, waiving its right to further written notice and opportunity for hearing under the provisions of Section 40-312(3), of the Idaho Code.
Bonneville County finds:
Certain utility facilities owned by the Company are located within the construction limits of the proposed project. The construction of this project is neither feasible from an engineering nor traffic safety standpoint with the utility facilities in their present location. It is necessary that these utility facilities be removed, relocated, or adjusted as shown by the attached plans.
THEREFORE, IT IS HEREBY ORDERED:
1. Certain utility facilities owned by the Company be removed, relocated, or adjusted as shown by the plans.
2. The Company shall accomplish the work prior to work on the above captioned project begins.
3. All relocation work must be completed no later than March 1st, 2021. Should work not be completed by this date, an administrative fee of $500 will be assessed per Calendar Day until the work is complete. This fee will be paid directly to Bonneville County.
4. The removal, relocation, or adjustment of these utility facilities is to be coordinated with the Resident Engineer. The Company shall give the Resident Engineer at least forty-eight (48) hours advance notice of intention to start work or to resume work subsequent to suspension. The resident engineer may be contacted at: 
Kevin Kuther, P.E., Resident Engineer
Local Highway Technical Assistance Council (LHTAC)
3330 Grace Street
Boise, ID 83703
Phone: (208)-344-0565
Email: kkuther@lhtac.org
5. The Company shall verify with the Resident Engineer, prior to using road right-of-way being acquired for this construction project for relocation of utility facilities, that Bonneville County has obtained right of access and construction activities are allowed on the property.
6. The Company shall provide traffic control consistent with the plans. During the progress of the utility work such barricades, lights, and other traffic control devices shall be erected and maintained as may be necessary or as may be directed for the protection of the traveling public. Barricades, lights, and other traffic control devices shall conform to the current issue of the Manual on Uniform Traffic Control Devices for Streets and Highways. Parked equipment and stored materials shall be as far from the traveled way as feasible. Items left overnight within 30 feet of the travel way shall be marked and/or protected.
7. Any and all work required to complete this relocation of facilities will be paid by the Company. The above captioned project will make no accommodations or monetary contributions for this work. 
8. The Company shall indemnify, defend, and hold harmless Bonneville County and its officers, agents, and employees against all liability, loss, and costs arising from actions, suits, claims, or demands arising from performance of this order.
9. The Company shall bear the cost and be responsible for repairing any damage caused by the work and shall be responsible for all of their actions. Bonneville County shall bear no responsibility if any cause arises due to Company’s actions.
10. Bonneville County shall not be responsible for any costs associated with the Company’s execution of these contemplated actions.
11. Commencement of activities contemplated in this Order shall constitute acceptance of terms.
The COMPANY must acknowledge that if compensable work on this project is required by COMPANY, all materials must meet current Build America, Buy America (BABA) requirements. Payment will not be made without proper certification.

Dated this	 day of		 	, 2020.

	Bonneville County

	By:						
	LOCAL OFFICIAL
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