## MTR Template
LILB Minimum Testing Requirements
The requirements listed in this document are contractual and must be provided for acceptance and payment.
Form numbers as listed will be required for material acceptance. Substitution of forms will not be allowed.
Volume units must be measured by Contractor survey for acceptance.
Products, with the exception of those within specification sections 503, 505, 512, 612, and 613, can be accepted by inclusion on the ITD QPL. QPL print out required for project files.
BID # | MATERIAL | PURPOSE OF TESTING | SPEC. REF. | TEST METHOD | REQUIRED REPORT FORM NO. | MINIMUM FREQUENCY | REMARKS, NOTES, OR ADDITIONAL INSTRUCTIONS | BID QUANTITY | MINIMUM NO. TESTS/ CERTS REQ.
|  |  | SAMPLED BY | TESTED BY
BID ITEM NO. & DESCRIPTION: 205-005A - Excavation
205-005A | Excavation Class C Compaction Excavated to top of Subgrade or below natural ground under embankments | ACCEPTANCE In-Place Density | 205.03F | AASHTO T 99 AASHTO T 180 AASHTO T 272 Idaho IT-74 |  |  | RE to document compaction effort/proof roll.
|  |  | Project Personnel | Project Personnel
| Excavation Subgrade Embankment Fill |  | 205.03F | AASHTO T 99 AASHTO T 180 AASHTO T 272 Idaho IT-74 AASHTO T 310 | ITD-850 | Each 2,500 CY or 4,000 tons but not less than one test per lift for each bottom two and each top lift and no less than one test per three lifts. | Document Compaction effort (equipment, number of passes etc.) for lifts not tested. After remedial efforts, obtain check tests withing 10 feet and at same depth as original test.
|  |  | Contractor | Contractor
BID ITEM NO. & DESCRIPTION: 205-030A - Borrow
205-030A | Borrow | ACCEPTANCE In-Place Density | 205.03F | AASHTO T 99 AASHTO T 180 AASHTO T 272 Idaho IT-74 AASHTO T 310 | ITD-850 | Each 2,500 CY or 4,000 tons but not less than one test per lift for each bottom two and each top lift and no less than one test per three lifts. | Document Compaction effort (equipment, number of passes etc.) for lifts not tested. After remedial efforts, obtain check tests withing 10 feet and at same depth as original test.
|  |  | Contractor | Contractor
BID ITEM NO. & DESCRIPTION: 205-040A - Granular Borrow
205-040A | Granular Borrow | ACCEPTANCE In-Place Density | 205.03F | AASHTO T 99 AASHTO T 180 AASHTO T 272 Idaho IT-74 AASHTO T 310 | ITD-850 | Each 5,000 CY but not less than one test per lift for each bottom 3 and each top 3 lifts | Document Compaction effort (equipment, number of passes etc.) for lifts not tested. After remedial efforts, obtain check tests withing 10 feet and at same depth as original test.
|  |  | Contractor | Contractor
|  | ACCEPTANCE Sand Equivalent | 205.02 | AASHTO T 27 AASHTO T 11 AASHTO T 176 | ITD-901 | Each 10,000 CY | Sand equivalent requirements do not apply to RAP used as Granular Borrow
|  |  | Contractor | Contractor
BID ITEM NO. & DESCRIPTION: 205-100A - Guardrail Terminal Grading
205-100A | Aggregate | ACCEPTANCE In-Place Density | 303.02 703.04 | FOP for AASHTO T-310 Method B | ITD-850 | Each 1,000 Tons | Class D compaction
|  |  | Contractor | Contractor
BID ITEM NO. & DESCRIPTION: 210-015A - Compacting Backfill
210-015A | Compacting Backfill | ACCEPTANCE In-Place Density | 210.03 | AASHTO T 99 AASHTO T180 AASHTO T 272 Idaho IT-74 AASHTO T 310 Method B | ITD-850 | Each 2,500 CY or 4,000 tons for each structure component. Abutments for Bridge approach slabs not less than one test per 2 8in compacted lift. | Document compaction effort for each lift. Obtain check tests within 10 feet (3m) and at same depth as original test.
|  |  | Contractor | Contractor
BID ITEM NO. & DESCRIPTION: 215-050A - Geosynthetic Reinforced Abutment Backfill
215-005A | Aggregate | ACCEPTANCE Gradation Sand Equivalent Fracture Count | 303.02 703.04 | FOP for AASHTO R 90 FOP for AASHTO R 76 FOP for AASHTO T 27 FOP for AASHTO T 11 FOP for AASHTO T 255 FOP for AASHTO T 265 FOP for AASHTO T 176 Alt. Method 2, Mechanical FOP for AASHTO T 335 Method 1 | ITD-901 | Each 700 CY or 1,000 Tons
|  |  | Contractor | Contractor
|  | ACCEPTANCE In-Place Density | 215.03 | AASHTO T 180 Idaho IT-74 AASHTO T-310 Method B | ITD-850 | 1 test per 16 inches of backfill, per abutment | Contractor is responsible for providing an Idaho T-74 density curve
|  |  | Contractor | Contractor
| Subgrade Separation Geotextile | ACCEPTANCE Certification | 718.07 | ASTM D4632 ASTM D6241 ASTM D4533 ASTM D4751 ASTM D4491 | ITD-851 or 849 for Structural Applications or Inclusion on ITD QPL (requires print out of QPL for files) | Total Quantity Paid | Provide Manufacturer Certification
|  |  | Manufacturer | Manufacturer
BID ITEM NO. & DESCRIPTION: 301-010A - Granular Subbase
301-010A | Granular Subbase | ACCEPTANCE In-Place Density | 301.02 | AASHTO T 180 Idaho IT-74 AASHTO T 310 Method B | ITD-850 | No less than one per bridge approach | Contractor is responsible for providing an Idaho T-74 density curve
|  |  | Contractor | Contractor
|  | ACCEPTANCE Gradation Sand Equivalent | 301-02 703.11 | AASHTO R 90 AASHTO R 76 AASHTO T 27 AASHTO T 255 AASHTO T 265 AASHTO T 176 Alt Method 2, Mechanical | ITD-901 | Each 5,000 Tons or 3,000 CY | Acceptance from windrow or roadway. Wash method not required Moisture percent required for payment only
|  |  | Contractor | Contractor
BID ITEM NO. & DESCRIPTION: 303-022A - 3/4" Agg TY B for Base
303-022A | Aggregate | ACCEPTANCE Gradation Sand Equivalent Fracture Count | 303.02 703.04 | FOP for AASHTO R 90 FOP for AASHTO R 76 FOP for AASHTO T 27 FOP for AASHTO T 11 FOP for AASHTO T 255 FOP for AASHTO T 265 FOP for AASHTO T 176 Alt. Method 2, Mechanical FOP for AASHTO T 335 Method 1 | ITD-901 | Each 700 CY or 1,000 Tons | Acceptance from windrow or roadway. Moisture percent required for payment only
|  |  | Contractor | Contractor
| Compacted Roadway | ACCEPTANCE In-Place Density | 303.02 | AASHTO T 310 Method B | ITD-850 | Each 700 CY or 1,000 Tons, but no less than one per bridge approach | Contractor is responsible for providing an Idaho T-74 density curve
|  |  | Contractor | Contractor
BID ITEM NO. & DESCRIPTION: 401-020A - CSS-1 Diluted Emulsified Asphalt for Tack Coat
401-020A | CSS-1 Diluted Emulsified Asphalt for Tack Coat | ACCEPTANCE Certification | 702.03 702.05 | FOP for AASHTO R 66 AASHTO T 59 | Loading Certificate | Each individual truck, trailer, car or shipment to the project.
|  |  | Manufacturer | Manufacturer
BID ITEM NO. & DESCRIPTION: 405-XXX Superpave HMA SP-
405-XXX | Mix Design | APPROVED BY RE | 405.03.B | No Testing Required | Mix Design | 1 per project, per mix | For project quantities less than 500 Tons Roller pattern to be observed by the Engineer
Project Personnel
| Superpave HMA Production Paving | ACCEPTANCE Density (Method Spec) | 405.03 | Idaho IT 125 | ITD-891 | 1 per lift
|  |  | Contractor | Contractor
BID ITEM NO. & DESCRIPTION: 405-XXX Superpave HMA SP-
405-XXXA | Mix Design | APPROVED BY RE | 4050.03.B | No Testing Required | Mix Design | 1 per project, per mix | For project quantities more than 500 Tons
Project Personnel
| Superpave HMA Production Paving | ACCEPTANCE Loose Mix from Roadway Asphalt Content Gradation Moisture | 405.03 | FOP for AASHTO R97* FOP for AASHTO R 47 FOP for AASHTO T 329 FOP for AASHTO T308 FOP for AASHTO T30 | ITD-833 | One test within the first 500 Tons, 1 test for every 750 Tons thereafter.
|  |  | Contractor | Contractor
|  | ACCEPTANCE Density (Percent Compaction) | 450.03 405.03-L | FOP for AASHTO R 67 FOP for AASHTO R 97* FOP for AASHTO T 166 Method A FOP for AASHTO T 331 FOP for AASHTO T 209 (Bowl Method) ASTM D7227 | ITD-773 ITD 892 | 5 Stratified Random Cores per project
|  |  | Contractor | Contractor
BID ITEM NO. & DESCRIPTION: 502-140A - Concrete CL 40A Sch. No. 1
502-140A | Concrete Ready Mix Plant Inspection |  | Project Personnel | Project Personnel | ITD-893 or equivalent | 1 per project | Inspection of plant is valid for 1 year
| Mix Design | ACCEPTANCE Admixtures (Approved List) | 709.02 709.03 709.04 709.05 | ATM C494 AASHTO M 154 | QPL
|  |  | Contractor | Contractor
| Cement | ACCEPTANCE Certification | 701.01 | AASHTO M 85 | Supplier Certification | Each week concrete is placed representing the amount used | Supplier Certification
|  |  | Manufacturer | Manufacturer
| Fly Ash | ACCEPTANCE Certification | 714 |  | Supplier Certification | Each week fly ash is placed representing the amount used | Supplier Certification
|  |  | Manufacturer | Manufacturer
| Concrete Production of 3,500 psi or greater | FIELD ACCEPTANCE Slump Air Content Temperature Unit Weight Cement Factor | 502.02 | WAQTC TM 2 AASHTO T 119 AASHTO T121 AASHTO 309 AASHTO T 152 | ITD-70 | First load, then randomly each 50 CY until quantity exceeds 100 CY. Thereafter randomly every 100 CY but not less than one per day.
|  |  | Contractor | Contractor
|  | ACCEPTANCE Compressive Strength Surface Resistivity | 502.02 | AASHTO T 22 AASHTO T 23 AASHTO T 358 | ITD-845 | 1 Set of three 28 day cylinders and 1 set of two 7 day cylinders. Not less than 1 per day. | A single sample of concrete must be sufficient size for cylinders, air, slump, and unit weight testing.
|  |  | Contractor | Contractor
BID ITEM NO. & DESCRIPTION: 502-XXXA - Prestressed Girder
502-XXXA | Concrete Ready Mix Plant Inspection |  | Project Personnel | Project Personnel | ITD-893 or equivalent | 1 per project
| Mix Design | ACCEPTANCE Admixtures (Approved List) | 709.02 709.03 709.04 709.05 | ATM C494 AASHTO M 154 | QPL
|  |  | Contractor | Contractor
| Cement | ACCEPTANCE Certification | 701.01 | AASHTO M 85 | Supplier Certification | Each week concrete is placed representing the amount used
|  |  | Manufacturer | Manufacturer
| Fly Ash | ACCEPTANCE Certification | 714 |  | Supplier Certification | Each week fly ash is placed representing the amount used
|  |  | Manufacturer | Manufacturer
| Pre-cast Stringers, Prestressed Members | ACCEPTANCE Field Tests Air Slump, Unit Weight, Temperature | 502.02 | AASHTO T119 AASHTO T152 AASHTO T309 AASHTO T121 | ITD-70 | One (1) per member
|  |  | Contractor or Supplier | Contractor or Supplier
|  | ACCEPTANCE Compressive Strength | 502.02 | AASHTO T22 AASHTO T23 | ITD-845 | One (1) set of three (3) 28-day cylinders per member
|  |  | Contractor or Supplier | Contractor or Supplier
| Metal Reinforcement, Prestressing Strand & Other Steel Parts | ACCEPTANCE Certification | 503.02 708.02 708.05 | AASHTO M 31 AASHTO A416 ASTM A722 | ITD-851 with mill test reports | Total Quantity Paid
|  |  | Manufacturer | Manufacturer
BID ITEM NO. & DESCRIPTION: 502-430A - Concrete Parapet
502-430A | Concrete Ready Mix Plant Inspection |  | Project Personnel | Project Personnel | ITD-893 or equivalent | 1 per project | Inspection of plant is valid for 1 year
| Mix Design | ACCEPTANCE Admixtures (Approved List) | 709.02 709.03 709.04 709.05 | ATM C494 AASHTO M 154 | QPL
|  |  | Contractor | Contractor
| Cement | ACCEPTANCE Certification | 701.01 | AASHTO M 85 | Supplier Certification | Each week concrete is placed representing the amount used | Supplier Certification
|  |  | Manufacturer | Manufacturer
| Fly Ash | ACCEPTANCE Certification | 714 |  | Supplier Certification | Each week fly ash is placed representing the amount used | Supplier Certification
|  |  | Manufacturer | Manufacturer
| Concrete Production of 3,500 psi or greater | FIELD ACCEPTANCE Slump Air Content Temperature Unit Weight Cement Factor | 502.02 | WAQTC TM 2 AASHTO T 119 AASHTO T121 AASHTO 309 AASHTO T 152 | ITD-70 | First load, then randomly each 50 CY until quantity exceeds 100 CY. Thereafter randomly every 100 CY but not less than one per day.
|  |  | Contractor | Contractor
|  | ACCEPTANCE Compressive Strength Surface Resistivity | 502.02 | AASHTO T 22 AASHTO T 23 AASHTO T 358 | ITD-845 | 1 Set of three 28 day cylinders and 1 set of two 7 day cylinders. Not less than 1 per day. | A single sample of concrete must be sufficient size3 for cylinders, air, slump, and unit weight testing.
|  |  | Contractor | Contractor
| Metal Reinforcement | ACCEPTANCE Certification | 503.02 708.02 | AASHTO M 31 | Mill Certification with Field Tags | Total Quantity Paid | Provide Manufacturer Certification
|  |  | Manufacturer | Manufacturer
BID ITEM NO. & DESCRIPTION: 502-465A - Prestressed Slabs (4' x 1'3")
502-465A | Pre-cast Stringers, Prestressed Members | FIELD ACCEPTANCE Slump Air Content Temperature Unit Weight | 502.02 | AASHTO T119 AASHTO T152 AASHTO T309 AASHTO T121 | ITD-70 | One (1) per member
|  |  | Contractor | Contractor
|  | ACCEPTANCE Compressive Strength | 502.02 | AASHTO T22 AASHTO T23 | ITD-845 | One (1) set of three (3) 28-day cylinders and One (1) set of two (2) 7-day cylinders per member
|  |  | Contractor | Contractor
| Reinforcing Steel and Prestressing Steel | ACCEPTANCE Certification | 503.02 708.02 | AASHTO M 31 | Mill Certification with Field Tags | Total Quantity Paid | Provide Manufacturer Certification
|  |  | Manufacturer | Manufacturer
BID ITEM NO. & DESCRIPTION: 502-XXXA - Voided Slabs, Approach Slabs
502-XXXA | Voided Slabs, Approach Slabs | FIELD ACCEPTANCE Slump Air Content Temperature Unit Weight | 502.02 | AASHTO T119 AASHTO T152 AASHTO T309 AASHTO T121 | ITD-70 | One (1) per member/slab or when multiple members are poured in one continuous line - one test per line up to 50cy and additional tests every 50cy thereafter.
|  |  | Contractor | Contractor
|  | ACCEPTANCE Compressive Strength | 502.02 | AASHTO T22 AASHTO T23 | ITD-845 | One set of cylinders per member/slab or when multiple members are poured in one continuous line - one set of cylinders per line up to 50cy and additional tests every 50cy thereafter.
|  |  | Contractor | Contractor
| Reinforcing Steel | ACCEPTANCE Certification | 503.02 708.02 | AASHTO M 31 | Mill Certification with Field Tags | Total Quantity Paid | Provide Manufacturer Certification
|  |  | Manufacturer | Manufacturer
BID ITEM NO. & DESCRIPTION: 503-005A - Metal Reinforcement Schedule No. 1
503-005A | Metal Reinforcement Schedule No. 1 | ACCEPTANCE Certification | 503.02 708.02 | AASHTO M 31 | Mill Certification with Field Tags | Total Quantity Paid | Provide Manufacturer Certification
|  |  | Manufacturer | Manufacturer
BID ITEM NO. & DESCRIPTION: 503-020A - Epoxy Coated Metal Reinforcement
503-020A | Epoxy Coated Metal Reinforcement | ACCEPTANCE Certification | 503.02 708.02 | AASHTO M 31 | Mill Certification with Field Tags | Total Quantity Paid | Provide Manufacturer Certification
|  |  | Manufacturer | Manufacturer
BID ITEM NO. & DESCRIPTION: 504-010A - Structural Steel
504-010A | Structural Steel | ACCEPTANCE Certification | 504.01 504.03 708.06 | AASHTO M 270 | Mill Certification with Field Tags | Total Quantity Paid | Provide Manufacturer Certification
|  |  | Manufacturer | Manufacturer
BID ITEM NO. & DESCRIPTION: 504-XXX - Pedestrian Bicycle Railing / Combined Ped/Bicycle Traffic Railing
504-XXX | Pedestrian Bicycle Railing Combined Ped/Bicycle Traffic Railing | ACCEPTANCE Certification | 504.02 708.06-1 | AASHTO M 270 | ITD-851 | Total Quantity Paid | Provie Manufacturer Certification
|  |  | Manufacturer | Manufacturer
BID ITEM NO. & DESCRIPTION: 504-050A - 3 Tube Curb Mount Rail
504-050A | 3 Tube Curb Mount Rail | ACCEPTANCE Certification | 504.02 708.06-1 | AASHTO M 270 | ITD-851 | Total Quantity Paid | Provide Manufacturer Certification
|  |  | Manufacturer | Manufacturer
BID ITEM NO. & DESCRIPTION: 505-110A - Provide & Drive 16" Diameter Steel Shell Pile
505-110A | Provide & Drive 16" Diameter Steel Shell Pile | ACCEPTANCE Certification | 505.02 708.30 | ASTM A36 | Mill Certification with Field Tags | Total Quantity Paid | Provide Manufacturer Certification
|  |  | Manufacturer | Manufacturer
BID ITEM NO. & DESCRIPTION: 505-160A - Provide & Drive Test Steel Shell Pile 16"
505-160A | Provide & Drive Test Steel Shell Pile 16" | ACCEPTANCE Certification | 505.02 708.30 | ASTM A36 | Mill Certification with Field Tags | Total Quantity Paid | Provide Manufacturer Certification
|  |  | Manufacturer | Manufacturer
BID ITEM NO. & DESCRIPTION: 506-XXX - Pre-Stressing Strand
506-XXX | Pre-Stressing Strand | ACCEPTANCE Certification | 708.05 | ASTM A416 ASTM A722 | ITD-851 | Total Quantity Paid | Provide Manufacturer Certification
|  |  | Manufacturer | Manufacturer
BID ITEM NO. & DESCRIPTION: 509-005A - Non-Structural Concrete
509-005A | Non Structural Concrete | ACCEPTANCE Testing | 509.02 |  | Passing QC Breaks | Total Quantity Paid
|  |  | Concrete Supplier | Concrete Supplier
BID ITEM NO. & DESCRIPTION: 511-005A - Concrete Waterproof System TY D
511-005A | Concrete Waterproof System TY D | ACCEPTANCE Visual | No Testing Required | No Testing Required | ITD-851 | Total Quantity Paid | Provide Manufacturer Submittal
BID ITEM NO. & DESCRIPTION: 519-005A - Concreted Pile
519-005A | Concrete | ACCEPTANCE Certification | 502.02(B) |  | ITD-851 | Total Quantity Paid
|  |  | Concrete Supplier | Concrete Supplier
| Steel Pile | ACCEPTANCE Certification | 505.02 708.30 | ASTM A36 | ITD-851 | Total Quantity Paid | Provide Manufacturer Certification
|  |  | Manufacturer | Manufacturer
BID ITEM NO. & DESCRIPTION: 522-005A - Controlled Density Fill
522-005A | Controlled Density Fill | ACCEPTANCE Certification | 522.02 |  | Mix Design, RE Approved | 1 per project
|  |  | Contractor | Contractor
BID ITEM NO. & DESCRIPTION: 551-005A - Prepared & Placed PPC Overlay
551-005A | Prepared & Placed PPC Overlay | ACCEPTANCE Certification |  |  | ITD-851 | Total Quantity Paid | Provide Manufacturer Certification
|  |  | Manufacturer | Manufacturer
BID ITEM NO. & DESCRIPTION: 560-005A - Dewatering Foundation
560-005A | Dewatering Foundation | ACCEPTANCE Visual | No Testing Required | No Testing Required | Stamped Dewatering Plan | Total Quantity Paid
BID ITEM NO. & DESCRIPTION: 578-005A - Precast Concrete Culvert
578-005A | Precast Concrete Culvert | ACCEPTANCE Certification | 706.01 706.04 |  | ITD-851 | Total Quantity Paid | Provide Manufacturer Certification
|  |  | Manufacturer | Manufacturer
BID ITEM NO. & DESCRIPTION: 584-005a Temporary Shoring
584-005a | Temporary Shoring | ACCEPTANCE Visual | No Testing Required | No Testing Required | ITD-854 | Total Quantity Paid | RE Letter - See QA Manual Section 250.00 | 1.0 LS | RE-LETTER
| Test No. | Test Date | Form Used | Accept/ Verify. | Qty. | P/F | Remarks
BID ITEM NO. & DESCRIPTION: 586-005a Utility Conduit
586-005a | Utility Conduit | ACCEPTANCE Certification | 586.02 |  | ITD-854 or 851 for steel | Total Quantity Paid | Submit Manufacturer Certification | 1.0 LS | CERT
|  |  | Manufacturer | Manufacturer
| Test No. | Test Date | Form Used | Accept/ Verify. | Qty. | P/F | Remarks
BID ITEM NO. & DESCRIPTION: 602-XXX - Pipe Culvert
602-XXX | Concrete Pipe | ACCEPTANCE Certification | 502.01(B) |  | Supplier Certification | Total Quantity Paid | Concrete Supplier Certification
|  |  | Concrete Supplier | Concrete Supplier
| PVC/HDPE/Steel Pipe | ACCEPTANCE Visual | No Testing Required | No Testing Required | Supplier Certification | Total Quantity Paid
| Fly Ash | ACCEPTANCE Certification | 714 |  | Supplier Certification | Each week concrete is placed representing the amount used | Concrete Supplier Certification
|  |  | Manufacturer | Manufacturer
| Concrete Production of 3,500 psi or greater | FIELD ACCEPTANCE Slump Air Content Temperature Unit Weight Cement Factor | 502.02 | WAQTC TM 2 AASHTO T 119 AASHTO T121 AASHTO 309 AASHTO T 152 | ITD-70 | First load, then randomly each 50 CY until quantity exceeds 100 CY. Thereafter randomly every 100 CY but not less than one per day.
|  |  | Contractor | Contractor
|  | ACCEPTANCE Compressive Strength Surface Resistivity | 502.02 | AASHTO T 22 AASHTO T 23 AASHTO T 358 | ITD-845 | 1 Set of three 28 day cylinders and 1 set of two 7 day cylinders. Not less than 1 per day. | A single sample of concrete must be sufficient size3 for cylinders, air, slump, and unit weight testing.
|  |  | Contractor | Contractor
BID ITEM NO. & DESCRIPTION: 608-XXX - Apron for Pipe
608-XXX | Concrete Aprons | ACCEPTANCE Certification | 706.01 706.02 706.03 |  | ITD-851 | Total Quantity Paid | Concrete Supplier Certification
|  |  | Concrete Supplier | Concrete Supplier
| PVC/HDPE/Steel Aprons | ACCEPTANCE Visual | No Testing Required | No Testing Required | ITD-851 | Total Quantity Paid
| Fly Ash | ACCEPTANCE Certification | 714 |  | Supplier Certification | Each week concrete is placed representing the amount used | Supplier Certification
|  |  | Manufacturer | Manufacturer
| Concrete Production of 3,500 psi or greater | FIELD ACCEPTANCE Slump Air Content Temperature Unit Weight Cement Factor | 502.02 | WAQTC TM 2 AASHTO T 119 AASHTO T121 AASHTO 309 AASHTO T 152 | ITD-70 | First load, then randomly each 50 CY until quantity exceeds 100 CY. Thereafter randomly every 100 CY but not less than one per day.
|  |  | Contractor | Contractor
|  | ACCEPTANCE Compressive Strength Surface Resistivity | 502.02 | AASHTO T 22 AASHTO T 23 AASHTO T 358 | ITD-845 | 1 Set of three 28 day cylinders and 1 set of two 7 day cylinders. Not less than 1 per day. | A single sample of concrete must be sufficient size for cylinders, air, slump, and unit weight testing.
|  |  | Contractor | Contractor
BID ITEM NO. & DESCRIPTION: 609-XXXA - Minor Structures
609-XXXA | Concrete 3,000 psi or less | ACCEPTANCE Certification | 509 |  | Passing QC Breaks | Total Quantity Paid
|  |  | Concrete Supplier | Concrete Supplier
BID ITEM NO. & DESCRIPTION: 612 Metal Guardrail Items (612-005A, 612-110A, 612-115C, 612-120B)
612-005A, 612-110A, 612-115C, 612-120B | Post and Blocks | ACCEPTANCE Certification | 710.03 710.09 |  | ITD-851 | Total Quantity Paid | Provide Manufacturer MASH/NCHRP Certification
|  |  | Manufacturer | Manufacturer
| Steel Rail and Fittings | ACCEPTANCE Certification | 708.14 |  | ITD-851 | Total Quantity Paid | Provide Manufacturer MASH/NCHRP Certification
|  |  | Manufacturer | Manufacturer
| Aluminum Rail and Fittings | ACCEPTANCE Certification | 708.25 |  | ITD-851 | Total Quantity Paid | Provide Manufacturer MASH/NCHRP Certification
|  |  | Manufacturer | Manufacturer
| Metal Terminal Section | ACCEPTANCE Certification | Drawings |  | ITD-851 | Total Quantity Paid | Provide Manufacturer MASH/NCHRP Certification
|  |  | Manufacturer | Manufacturer
BID ITEM NO. & DESCRIPTION: 613-030A - Crash Cushion, Partially Reusable
613-030A | Concrete | ACCEPTANCE Certification | 509 |  | Passing QC Breaks | Total Quantity Paid | See QPL for list of acceptable devices
|  |  | Concrete Supplier | Concrete Supplier
| Device | ACCEPTANCE Visual | No Testing Required | No Testing Required
BID ITEM NO. & DESCRIPTION: 614-015A - Sidewalks
614-015A | Concrete | ACCEPTANCE Certification | 509 |  | Passing QC Breaks | Total Quantity Paid
|  |  | Concrete Supplier | Concrete Supplier
BID ITEM NO. & DESCRIPTION: 615-XXX - Curb and Gutter
615-XXX | Concrete | ACCEPTANCE Certification | 509 |  | Passing QC Breaks | Total Quantity Paid
|  |  | Concrete Supplier | Concrete Supplier
BID ITEM NO. & DESCRIPTION: 616-010A - Sign TY B-1
616-010A | Sign TY B-1 | ACCEPTANCE Certification | 712.02 Reflective Sheeting |  | ITD-851 | Total Quantity Paid | Provide Manufacturer Certification
|  |  | Manufacturer | Manufacturer
BID ITEM NO. & DESCRIPTION: 622-030A - 15" Precast Concrete Headgate
622-030A | 15" Precast Concrete Headgate | ACCEPTANCE Certification | 502.01-B |  | ITD-851 | Total Quantity Paid | Provide Manufacturer Certification
|  |  | Manufacturer | Manufacturer
BID ITEM NO. & DESCRIPTION: 640-XXX - Geosynthetics
640-XXX | Riprap/Erosion Control Geotextile, Drainage Geotextile, Riprap/Erosion Control Geotextile, Subgrade Separation Geotextile | ACCEPTANCE Certification | 718.07 | ASTM D4632 ASTM D6241 ASTM D4533 ASTM D4751 ASTM D4491 | ITD-851 or 849 for Structural Applications or Inclusion on ITD QPL (requires print out of QPL for files) | Total Quantity Paid | Provide Manufacturer Certification
|  |  | Manufacturer | Manufacturer
BID ITEM NO. & DESCRIPTION: 677-005A - Record Drawings
677-005A | Record Drawings | ACCEPTANCE Visual | No Testing Required | No Testing Required | Stamped As-Built Plans | Total Quantity Paid
BID ITEM NO. & DESCRIPTION: S500-11A - SP Dewatering Foundation - Coffer Dams
S500-11A | 24" Pipe Culvert | ACCEPTANCE Visual | No Testing Required | No Testing Required | Stamped Dewatering Plan | Total Quantity Paid
| Loose Riprap | ACCEPTANCE Visual | No Testing Required | No Testing Required |  | Total Quantity Paid | Initial Testing required for Apparent Specific Gravity, Absorption & Coarse Durability Index
| Visqueen | ACCEPTANCE Visual | No Testing Required | No Testing Required |  | Total Quantity Paid
BID ITEM NO. & DESCRIPTION: S501-20B - SP Bridge - Eco Block Half
S501-20B | SP Bridge - Eco Block Half | ACCEPTANCE Certification | S501-20B SP Bridge - Eco Block Half |  | ITD-851 | Total Quantity Paid | Provide Manufacturer Certification
|  |  | Project Personnel | Project Personnel
BID ITEM NO. & DESCRIPTION: S501-20C - SP Bridge - Eco Block Full Flat Cap
S501-20C | SP Bridge - Eco Block Full Flat Cap | ACCEPTANCE Certification | S501-20C SP Bridge - Eco Block Full Flat Cap |  | ITD-851 | Total Quantity Paid | Provide Manufacturer Certification
|  |  | Manufacturer | Manufacturer
BID ITEM NO. & DESCRIPTION: S501-25A - Bridge GRS-IBS Abutment
S501-25A | Aggregate | ACCEPTANCE Gradation Sand Equivalent Fracture Count | 303.02 703.04 | AASHTO R 90 AASHTO R 76 AASHTO T 27 AASHTO T 11 AASHTO T 255 AASHTO T 265 AASHTO T 176 Alt. Method 2, Mechanical AASHTO T335 Method 1 | ITD-901 | Every 700 CY or 1,000 Tons
|  |  | Contractor | Contractor
| Subgrade Separation Geotextile | ACCEPTANCE Certification | 718.07 | ASTM D4632 ASTM D6241 ASTM D4533 ASTM D4751 ASTM D4491 | ITD-851 or Inclusion on ITD QPL (requires print out of QPL for files) | Total Quantity Paid | Provide Manufacturer Certification
|  |  | Manufacturer | Manufacturer
IF YOUR PROJECT INCLUDES A STRUCTURAL ITEM THAT IS NOT LISTED IN THIS TEMPLATE, PLEASE REACH OUT TO LHTAC (DELETE THIS NOTE)

## Change Log
Date Version | Item | Change
2025.10.24
| All Fabrics | Updated structural fabrics to all either be accepted by 851 or 849.
| 303-022A | Added frequency for compaction reqs
| 405 | 405 less than 500 tons, added note in minimum frequency to require an 891 per lift.
| 502-430A | Acceptance, Strength, had a typo in the remarks "3" removed.
| 502-430A | Added reinforcement acceptance
| 502-465A | Added reinforcement acceptance
| 504-XXX | Added railing req's for combo and ped rails
| 519-005A | Added cert acceptance criteria for pile
| 602-XXX | Had a typo in the remarks "3" removed. Added visual as acceptance on pipe materials not previously included.
| 608-025A | Had a typo in the remarks "3" removed.
| 608-XXX | Had a typo in the remarks "3" removed. Added visual as acceptance on apron materials not previously included.
| 615-XXX | Added item and acceptance criteria
| S911-05A | Added section for concrete accepted by 25.
| 626-010A | Added Provide Manufacturer MASH/NCHRP Certification
| S904-05A | Added Provide Manufacturer MASH/NCHRP Certification on Devices
2025.11.18
| 502-465A | Added 7 day QC breaks
| 502-xxxA | Added 7 day QC breaks
2025.11.24
| 502-XXXA | Decreased frequency for multiple members in continuous pour.
2026.01.13
Added form number requirement to header of sheet
2026.01.21
| 502-465A | Removed "QC"
| 502-xxxA | Removed "QC"
2026.01.28
| 502-465A | Added Reinforcing Steel and Prestressing Steel acceptance requirements
| 502-xxxA | Added Reinforcing Steel acceptance requirements
2026.04.06
Updated formating
2026.07.10
| Various | Deleted various items previously listed as acceptance by ITD 25. Reduce confusion with Contractors, it's known observation is to take place.
| 502-XXXA | Added Item for Prestressed Girders
2026.08.05
| 215-005A | Updated minimum frequency requirements